## How to use
Remodeling Job Cost Tracker — how to use
What this is
One sheet per job. It compares what you budgeted for each cost code with what you have actually spent, and forecasts your final gross margin while the job is still open.
Which cells to edit
Yellow cells with blue text are inputs. Type over them. Everything else is a formula — leave it alone.
Steps
1. On the 'Job Cost Tracker' tab, enter the job name, contract price, approved change orders, your target gross margin and your labor burden multiplier.
2. List each cost code with its budget (from your estimate). Use one row per line item; there is room for 27 lines.
3. Committed = signed subcontracts and purchase orders not yet invoiced. It is what you owe even if the bill hasn't arrived.
4. For labor lines, enter hours worked and the worker's base hourly wage. The sheet multiplies by your burden multiplier, so labor cost includes payroll taxes, workers' comp and insurance.
5. For materials, subcontractors, equipment and other costs, enter invoiced or paid amounts in 'Other actual'.
6. Update it weekly. The summary shows budget used, an alert at 70%, 85% and 95% of budget, and your projected margin against target.
Notes
• The rows filled in are a SAMPLE kitchen remodel so you can see the format. Replace them with your own job.
• Forecast final cost is conservative: for each line it takes the highest of budget, committed and actual, assuming nothing will finish under budget.
• Labor burden multiplier: 1.35 means every $1.00 of wages costs you $1.35. Work out your own with the free calculator at remodelfin.com/calculators/labor-burden-calculator/
• Percentages are stored as fractions: type 25% or 0.25 for a 25% margin.
Free template from RemodelFin (remodelfin.com). RemodelFin does this automatically: crews log hours and receipts from the field and the job's margin updates as costs post.

## Job Cost Tracker
Job Cost Tracker
Summary
Job name | Sample: Kitchen remodel — 14 Oak St |  |  | Revenue (contract + change orders) | 78000
Contract price ($) | 78000 |  |  | Budgeted cost | 60500
Approved change orders ($) | 0 |  |  | Actual cost to date | 59523.5
Target gross margin | 25% |  |  | Budget used | 98.39%
Labor burden multiplier | 1.35 |  |  | Budget alert | 95% of budget used
|  |  |  | Forecast final cost | 62412.5
|  |  |  | Projected gross profit | 15587.5
|  |  |  | Projected gross margin | 19.98%
|  |  |  | Margin vs target | -5.016%
Cost code | Description | Category | Budget ($) | Committed ($) | Labor hours | Base wage ($/hr) | Other actual ($) | Actual cost ($) | Forecast final ($) | Variance to date ($) | % of budget used | Alert
01-L | Demo & site prep | Labor | 3200 | 0 | 70 | 30 | 0 | 2835 | 3200 | -365 | 88.59% | 85%
01-L | Framing | Labor | 8400 | 0 | 225 | 30 | 0 | 9112.5 | 9112.5 | 712.5 | 108.5% | OVER
01-L | Tile work | Labor | 4800 | 0 | 140 | 30 | 0 | 5670 | 5670 | 870 | 118.1% | OVER
01-L | Finish & trim | Labor | 3600 | 0 | 52 | 30 | 0 | 2106 | 3600 | -1494 | 58.5%
02-M | Lumber & sheathing | Materials | 6500 | 6200 | 0 | 0 | 6050 | 6050 | 6500 | -450 | 93.08% | 85%
02-M | Tile & flooring | Materials | 4200 | 4200 | 0 | 0 | 4380 | 4380 | 4380 | 180 | 104.3% | OVER
02-M | Cabinets & millwork | Materials | 11000 | 11000 | 0 | 0 | 10800 | 10800 | 11000 | -200 | 98.18% | 95%
02-M | Fixtures & hardware | Materials | 3800 | 3800 | 0 | 0 | 3950 | 3950 | 3950 | 150 | 103.9% | OVER
03-S | Electrical | Subcontractor | 7500 | 7500 | 0 | 0 | 7500 | 7500 | 7500 | 0 | 100% | OVER
03-S | Plumbing | Subcontractor | 5200 | 5200 | 0 | 0 | 4900 | 4900 | 5200 | -300 | 94.23% | 85%
04-E | Dumpster rental | Equipment | 900 | 900 | 0 | 0 | 900 | 900 | 900 | 0 | 100% | OVER
05-O | Permits & fees | Other | 1400 | 1400 | 0 | 0 | 1320 | 1320 | 1400 | -80 | 94.29% | 85%
[8 empty] | 0 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
TOTAL |  |  | 60500 | 40200 | 487 |  | 39800 | 59523.5 | 62412.5 | -976.5 | 98.39%
Note on B7: Wages x this = true labor cost. 1.35 means taxes, workers' comp and insurance add 35% to base wage. Use your own figure.