## How to use
Schedule of Values & Draw Request — how to use
What this is
A schedule of values (SOV) and progress-billing worksheet in the familiar AIA-style continuation-sheet layout, plus a one-page summary that works out how much to bill this period after retainage.
Which cells to edit
Yellow cells with blue text are inputs. Everything else is a formula.
Steps
1. On 'Pay Application', enter the project, application number, period end date, original contract sum, net change orders, retainage % and the total of all previous payment certificates.
2. On 'Schedule of Values', list each line item and its scheduled value. The scheduled values must add up to the contract sum to date; the summary shows a check.
3. Each draw: enter work completed this period and any materials stored on site but not yet installed. Move last draw's totals into 'From previous applications' before starting the next draw.
4. 'Current payment due' on the Pay Application tab is the amount to bill.
Notes
• The rows filled in are a SAMPLE $165,000 kitchen remodel at its second draw. Replace them with your own job.
• Retainage here is calculated on the total completed and stored to date, the usual method on AIA-style applications. Check your contract; some hold retainage on work only, or reduce it after 50% completion.
• Bill stored materials only with the documentation your contract requires, usually an invoice, proof of delivery and a lien waiver.
• This worksheet is not an official AIA document. If your contract requires AIA G702/G703 forms, use them for submission.
Free template from RemodelFin (remodelfin.com). RemodelFin builds SOV-based draw invoices from your job budget automatically.

## Pay Application
Application for Payment — Summary
Project | Sample: Kitchen remodel — 14 Oak St
Application no. | 2
Period to | 2026-09-30
Original contract sum ($) | 165000
Net change by change orders ($) | 0
Retainage % | 10%
Less previous certificates for payment ($) | 60480
Summary
1. Original contract sum |  | 165000
2. Net change by change orders |  | 0
3. Contract sum to date |  | 165000
4. Total completed & stored to date |  | 87250
5. Retainage |  | 8725
6. Total earned less retainage |  | 78525
7. Less previous certificates for payment |  | 60480
8. CURRENT PAYMENT DUE |  | 18045
9. Balance to finish, including retainage |  | 86475
Check: SOV total equals contract sum to date |  | OK
Note on B9: Total of all amounts certified on earlier applications. Sample: draw 1 billed $67,200 less 10% retainage = $60,480.

## Schedule of Values
Schedule of Values — Continuation Sheet
Application no. | 2 | Retainage % | 10%
Item | Description of work | Scheduled value ($) | From previous applications ($) | This period ($) | Materials presently stored ($) | Total completed & stored ($) | % complete | Balance to finish ($) | Retainage ($)
1 | General conditions / supervision | 12000 | 2400 | 2400 | 0 | 4800 | 40% | 7200 | 480
2 | Demolition | 8500 | 8500 | 0 | 0 | 8500 | 100% | 0 | 850
3 | Rough framing | 14200 | 14200 | 0 | 0 | 14200 | 100% | 0 | 1420
4 | Plumbing rough-in | 11800 | 11800 | 0 | 0 | 11800 | 100% | 0 | 1180
5 | Electrical rough-in | 9400 | 9400 | 0 | 0 | 9400 | 100% | 0 | 940
6 | HVAC rough-in | 6200 | 6200 | 0 | 0 | 6200 | 100% | 0 | 620
7 | Insulation | 4800 | 4800 | 0 | 0 | 4800 | 100% | 0 | 480
8 | Drywall & taping | 16500 | 9900 | 3300 | 0 | 13200 | 80% | 3300 | 1320
9 | Tile work | 18200 | 0 | 4550 | 0 | 4550 | 25% | 13650 | 455
10 | Cabinet installation | 22400 | 0 | 0 | 0 | 0 | 0% | 22400 | 0
11 | Countertops | 9800 | 0 | 0 | 9800 | 9800 | 100% | 0 | 980
12 | Plumbing finish | 7600 | 0 | 0 | 0 | 0 | 0% | 7600 | 0
13 | Electrical finish | 6400 | 0 | 0 | 0 | 0 | 0% | 6400 | 0
14 | Paint & finish carpentry | 11200 | 0 | 0 | 0 | 0 | 0% | 11200 | 0
15 | Punch list & final clean | 6000 | 0 | 0 | 0 | 0 | 0% | 6000 | 0
[6 empty] | 0 |  | 0 | 0
[6 empty] | 0 |  | 0 | 0
[6 empty] | 0 |  | 0 | 0
[6 empty] | 0 |  | 0 | 0
[6 empty] | 0 |  | 0 | 0
[6 empty] | 0 |  | 0 | 0
[6 empty] | 0 |  | 0 | 0
[6 empty] | 0 |  | 0 | 0
[6 empty] | 0 |  | 0 | 0
[6 empty] | 0 |  | 0 | 0
[6 empty] | 0 |  | 0 | 0
[6 empty] | 0 |  | 0 | 0
[6 empty] | 0 |  | 0 | 0
[6 empty] | 0 |  | 0 | 0
[6 empty] | 0 |  | 0 | 0
[6 empty] | 0 |  | 0 | 0
[6 empty] | 0 |  | 0 | 0
[6 empty] | 0 |  | 0 | 0
[6 empty] | 0 |  | 0 | 0
[6 empty] | 0 |  | 0 | 0
| GRAND TOTAL | 165000 | 67200 | 10250 | 9800 | 87250 | 52.88% | 77750 | 8725